## DASHBOARD
PROJECT PROGRESS DASHBOARD
Work Package ID | Package Code | Priority Level | Critical Path? | Eng Completion | Program Completion | Conduit & Wire Pulls | Devices Installed | PreComm Completed | BLOCKED - Eng Info | BLOCKED - Vendor Info | BLOCKED - Cond & Wire | BLOCKED - Devices | BLOCKED - PreComm | Active Change Orders? | Internal Gates Complete? | Open Punchlist Items | Open RFIs | Open Issues | Weekly Notes | Engineering Scope / Scope of Work

## SCOPE DASHBOARD
SCOPE DASHBOARD ¦ ENGINEERING REVIEW
Scope rows are manually identified by Scope ID. Values below are calculated; blocking X is human-managed. No automatic flag propagation.
Scope progress (H:K..M) is derived from WP PROGRESS: average of each column over work packages whose Primary Scope is this scope, each WP weighted equally. Blank and '--' are left out; enter 0 for 'in use, not started'. Blocked? (X) stays human-managed; 'Blocked WPs' is information only.
Scope ID | Engineering Scope | WP Count | Open Issues | Open RFIs | Blocked? (X) | Engineering State | Eng % | Prog % | Cond & Wire % | Device % | Loop Check % | PreComm % | WPs Gate Complete | Blocked WPs (count)

## WP PROGRESS
Work Package ID | Package Code | Primary Scope ID | Open Punch Items | Eng % Complete | Prog % Complete | Cond & Wire % Complete | Device Install % Complete | Loop Check % Complete | PreComm % Complete | C&E Values Received | CE Target Test Date | Engineering Completed? | Programming Completed? | Cond & Wire Completed? | Device Install Completed | Loops Check Completed | PreComm Complete? | Program Changes Required | Program changes Completed | Internal Progress Gates Complete? | Site Acceptance Test Complete? | Vendor Completed Checks | Blocked? (X) | Open RFIs | Open Engineering Issues | Progress Comments | Row Check (derived)

## BLOCKED ITEMS REPORT
PM / PE BLOCKED ITEMS REVIEW
Filter the Record ID column to nonblanks. Each X flag is independent; report does not set or clear flags.
Register | Record ID | Scope ID | Work Package ID(s) | Description / Question / Task | Owner | Status | Blocked (X)

## SCOPES
SCOPES ¦ Engineering System / Drawing / Logical Scope
Engineering scopes organize multiple Work Packages into a coherent functional system or issued drawing/logic package. Scope members and requirements are traced by ID.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Scope ID | Engineering Scope / System Description | Functional / Drawing Boundary | Lead Discipline / Responsible Party | Primary System ID (optional) | Related Work Package IDs (summary) | Disposition | Source / Requirement IDs | Engineering Basis / Authority | Review State | Engineering State | Engineering Progress % (if applicable) | Owner | Target Date | Related IDs | Notes | Updated | Work Actions

## WORK PACKAGES
Work Package ID | Package Code | Work Boundary Description | Parent Work Package ID (optional) | Primary Scope ID | Additional Scope IDs (optional) | Responsible Team / Person | Method / How | Deliverable | Depends On / Blocked By (IDs) | Progress Columns In Use | Tracking Basis | Supplemental Boundary Notes | Test Procedure Ref (optional) | Closeout Evidence Ref (optional) | Relationship Review State | Notes | Progress Row Check (derived)

## SYSTEM MODEL
SYSTEM MODEL ¦ Functional Systems
True functional System of Interest records (not the operational WORK PACKAGES progress grouping).
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
System ID | Source Code | System Name | System Type | Scope Disposition | Source IDs | Location / Boundary | Review State | Notes

## RFI REGISTER
RFI REGISTER ¦ Authoritative Working RFI Records
Persistent RFI IDs; one row per question. Counts use Primary WP ID to avoid double counting. Historical data requires owner review.
Statuses: Open / Submitted / Answered / Closed / Cancelled; all except Closed and Cancelled count as open. Blank WP remains Unassigned; do not infer.
RFI ID | Question / Clarification Requested | Status | Primary WP ID | Related WP IDs | Related Scope IDs | Source / Document Reference | Responsible Party | Requested By | Date Raised | Required By | Response / Decision | Response Source | Closed Date | Review State | Legacy Reference | Remarks | Blocked? (X)

## ISSUES
ISSUES ¦ Open Items and Findings
Technical findings / gaps needing engineering disposition; operational unfinished-work tasks stay in PUNCH LIST; formal client questions stay in RFI REGISTER.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Item ID | Kind | Statement | Affected IDs | Source IDs | Owner | Resolve By | Status | Priority | Opened Date | Closed Date | Resolution + Source | Legacy Reference | Notes | Primary Scope ID | Affected WP IDs | Blocked? (X)

## PUNCH LIST
Punchlist | Description | Discipline | Responsible Party | Work Package | Package Code (WP ID) | Priority Cat | Tag ID | DWG # | REF RFI # | Comments | Raised By | Raised Date | Cleared By | Cleared Date | Open / Close | AGE | CLEAR TIME | OLDER THAN 4WEEKS | OLDER THAN 6 WEEKS | OLDER THAN 8 WEEKS | Blocked? (X)
1 | [14 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
[15 empty] | Open |  |  | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
Open
Open
Open
Open
Open
Open
[15 empty] | Open |  |  | 1 | 1
[18 empty] | 1 | 1
[18 empty] | 1 | 1
[18 empty] | 1 | 1 | 1
[18 empty] | 1 | 1
1
1
1
1
[18 empty] | 1 | 1
Formulas:
AGE = IF([Open / Close]="","",IF([Open / Close]="Open",TODAY()-[Raised Date],"--"))

## REGISTRY GUIDE
READ ME ¦ Project Engineering Register v1.2 — Template Contract
Scopes define engineering groupings; WORK PACKAGES defines execution units; WP PROGRESS holds progress. DASHBOARD and SCOPE DASHBOARD are derived / managed views.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Section | Instruction | Owner / status
Template | PROJECT_PER_v1.2.xlsx is a reusable, BLANK project engineering register. Copy this file to approved project storage and assign an independent project revision. | Framework blank template v1.2
Authority | The project copy is an internal engineering/PM system of record. External contract, issued design and manufacturer documentation remain sources of truth with registered revisions. | Never supersede external source authority
Project data boundary | Do not populate or commit project records, prices, client names, private links or identifying site details into the public framework template. | Project data stays in project storage
Engineering Scope | SCOPES records functional, drawing or logical engineering scope. Trace individual requirements and source obligations in RECORDS; scopes group multiple implementation work packages. | Maintain stable Scope IDs
Work Package definition | WORK PACKAGES defines independently trackable execution units: ID, code, boundary, team, scope relationship, dependencies and delivery. It owns WP identifiers. SOV is OPTIONAL, not required. | Keep definition separate from progress
Work Package progress | WP PROGRESS contains user-entered progress, commissioning and blocking states, one row per WP ID. The row check and completion formulas are derived. | Use dropdown IDs; avoid duplicate progress rows
Progress meaning | 0–1 = numeric progress. -- = not used for this WP and excluded from completion and rollups. Blank = not entered. Unexpected text is flagged CHECK. | Do not treat blank as zero or complete
DASHBOARD identity | DASHBOARD column A contains manually assigned WP IDs. Do not auto-generate/reorder fixed rows by formulas; manual PM columns and weekly notes remain with that WP. | Manually maintain stable WP rows
DASHBOARD sorting | Sort/filter the entire DASHBOARD range (A:U), never a single column. Derived cells lookup by WP ID. Blocker flags, priority and notes are human-entered on dashboard. | Preserve row-level manual management
DASHBOARD layout | The five human-managed blocker categories, priority/critical path, change-order and weekly notes are presentation/PM controls; derived engineering/commissioning status comes from WP PROGRESS and registers. | Do not infer a blocker from an open count
Scope dashboard | SCOPE DASHBOARD summarizes engineering scopes using explicit Scope IDs and primary-scope WP associations. A scope blocking X is a separate human decision. | Status derivation, not acceptance
Blocked items report | BLOCKED ITEMS REPORT consolidates human-entered X flags; it never writes back to source registers or creates an engineering requirement. | Filter derived rows by nonblank Record ID
ISSUES | ISSUES records structural engineering unknowns, conflicts, design constraints, interface ambiguity and approvals. Stable IDs, source references and resolutions require traceability. | Engineering register, not punchlist
RFI authority | RFI REGISTER contains formal clarification requests, outgoing submission status and external responses. Engineering issues and punch-list actions are independently managed in their designated registers. | RFI status independent from Issue closure
PUNCH LIST | PUNCH LIST tracks operational actions, unfinished installation, checkout defects and test follow-up. Not a substitute for engineering ISSUES or formal RFIs. | Blocking is user-entered X
Sources and records | SOURCES holds accurate source/revision/locator. RECORDS holds atomic facts, requirements, constraints, assumptions, decisions and verification references. | Use source authority and review state
System model and links | SYSTEM MODEL registers functional systems. LINKS records typed relationships between records using stable IDs; explicit scope links are distinct from physical containment. | Source backed; no unsupported inference
Separate physical inventory | The official Equipment / Device / Points workbook remains a standalone engineering deliverable linked by Scope ID, WP ID, source IDs and related PER record IDs. | Use official EDP template
Intake and legacy | INTAKE QUEUE is a review queue for verbatim prior-work evidence, not automatically verified facts. Each project must start with empty intake rows. | Register and review prior work
Acceptance and baselines | Human engineering acceptance, project snapshot/configuration baseline, progress gate completion and project closeout are distinct events. CHANGE LOG and BASELINES are populated by authorized processes. | No approval implied by copying template
Template validation | Formula regression tests and blank-template checks are maintained within the framework repository, not included as project worksheets. Run framework QA before issuing modified blank templates. | See framework scripts/validate_blank_per.py
Formatting | Retain owner-established font/fill/color, validation, number format and conditional formatting conventions when creating project copies. Blue=editable, green=imported, orange=review and derived cells read-only. | Style-only revisions preserve structure
Initialization checks | Copy workbooks before use; check no foreign IDs, source records, notes, links, change events, responses, or hidden project data exists. Verify formulas, validations and dashboard lookup behavior. | Use framework sanitization/QA process
Source fidelity | Preserve exact external file names, document titles, folders, literal quotation and device-label text in source references. Human display labels may differ, but verbatim source quotes must not be silently renamed. | Traceability before presentation
Restrictions | Never assume a missing point, signal, contractual item, document or resource means zero, none or not applicable. Record explicitly unresolved quantities and dependencies. | Unknown does not mean excluded

## SOURCES
SOURCES ¦ Source Evidence
Source IDs and exact document issue/revision are required before facts or scope obligations are promoted.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Source ID | Document / File | Source Class | Issuer / Authority | Revision | Issue Date | Exact Locator / URL | Received Date | Governs / Topic | Review State | Supersedes ID | Notes

## RECORDS
RECORDS ¦ Engineering Evidence and Requirements
Typed durable Need/Fact/Requirement/Constraint/Criterion/Assumption/Directive/Decision/Finding records.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Record ID | Record Type | Atomic Statement | Applies To IDs | Source IDs | Authority / Binding Basis | Applicability | Confidence | Review State | Owner | Resolve By | Related IDs | Verification Method | Supersedes | Updated | Notes

## LINKS
LINKS ¦ Typed Relationships
Typed cross-record links; WorkPackage tracks_scope Scope links connect progress to contractual obligations.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Link ID | From Type | From ID | Relationship | To Type | To ID | Source IDs | Review State | Notes | Linked Scope State (derived)

## CHANGE LOG
CHANGE LOG ¦ Record Revision Events
Persistent change records must be written during an authorized process; this tab does not log edits automatically.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Change ID | Timestamp | Object Type | Object ID | Action | Old Rev / Value | New Rev / Value | By / Approved By | Source / Basis | Affected IDs | Notes

## BASELINES
BASELINES ¦ Immutable Snapshots
Register snapshot metadata only. Archive a separate immutable file and manifest; a baseline is not blanket approval.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Baseline ID | Milestone | Captured At | Authorized By | Register Revision | Source Manifest | SHA-256 / Hash | Storage Path | Status | Open Items | Notes

## INTAKE QUEUE
INTAKE QUEUE ¦ Legacy Notes and RFIs
Verbatim legacy prior-work content queued for M1/M2 comparison; neither verified nor promoted automatically.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Intake ID | Origin Tab | Origin Row | Verbatim Original Text | Legacy Status | Legacy System | Legacy Tag | Legacy Drawing | Legacy Comment | Suggested Kind | Review State | Promoted Record ID | Source ID | Legacy Cell