## DASHBOARD
PROJECT PROGRESS DASHBOARD
Work Package ID | Package Code | Priority Level | Critical Path? | Eng Completion | Program Completion | Conduit & Wire Pulls | Devices Installed | PreComm Completed | BLOCKED - Eng Info | BLOCKED - Vendor Info | BLOCKED - Cond & Wire | BLOCKED - Devices | BLOCKED - PreComm | Active Change Orders? | Internal Gates Complete? | Open Punchlist Items | Open RFIs | Open Issues | Weekly Notes | Engineering Scope / Scope of Work

## SCOPE DASHBOARD
SCOPE DASHBOARD ¦ ENGINEERING REVIEW
Scope rows are manually identified by Scope ID. Values below are calculated; blocking X is human-managed. No automatic flag propagation.
Scope progress (H:M) is derived from WP PROGRESS: average of each column over work packages whose Primary Scope is this scope, each WP weighted equally. Blank and '--' are left out; enter 0 for 'in use, not started'. Blocked? (X) stays human-managed; 'Blocked WPs' is information only.
Scope ID | Engineering Scope | WP Count | Open Issues | Open RFIs | Blocked? (X) | Engineering State | Eng % | Prog % | Cond & Wire % | Device % | Loop Check % | PreComm % | WPs Gate Complete | Blocked WPs (count)

## WP PROGRESS
Work Package ID | Package Code | Primary Scope ID | Priority Sequence | Open Punch Items | Eng % Complete | Prog % Complete | Cond & Wire % Complete | Device Install % Complete | Loop Check % Complete | PreComm % Complete | C&E Values Received | CE Target Test Date | Engineering Completed? | Programming Completed? | Cond & Wire Completed? | Device Install Completed | Loops Check Completed | PreComm Complete? | Program Changes Required | Program changes Completed | Internal Progress Gates Complete? | Site Acceptance Test Complete? | Vendor Completed Checks | Blocked? (X) | Open RFIs | Open Engineering Issues | Progress Comments | Row Check (derived)

## BLOCKED ITEMS REPORT
PM / PE BLOCKED ITEMS REVIEW
Filter the Record ID column to nonblanks. Each X flag is independent; report does not set or clear flags.
Register | Record ID | Scope ID | Work Package ID(s) | Description / Question / Task | Owner | Status | Blocked (X)

## SCOPES
SCOPES ¦ Engineering System / Drawing / Logical Scope
Engineering scopes organize multiple Work Packages into a coherent functional system or issued drawing/logic package. Scope members and requirements are traced by ID.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Scope ID | Engineering Scope / System Description | Functional / Drawing Boundary | Lead Discipline / Responsible Party | Primary System ID (optional) | Related Work Package IDs (summary) | Disposition | Source / Requirement IDs | Engineering Basis / Authority | Review State | Engineering State | Engineering Progress % (if applicable) | Owner | Target Date | Related IDs | Notes | Updated | Work Actions

## WORK PACKAGES
Work Package ID | Package Code | Work Boundary Description | Legacy Selector Label (compatibility) | Priority Sequence | Parent Work Package ID (optional) | Primary Scope ID | Additional Scope IDs (optional) | Responsible Team / Person | Method / How | Deliverable | Depends On / Blocked By (IDs) | Progress Columns In Use | Tracking Basis | Supplemental Boundary Notes | Test Procedure Ref (optional) | Closeout Evidence Ref (optional) | Relationship Review State | Notes | Progress Row Check (derived)

## RFI LEGACY (hidden)
Punchlist | Description | Discipline | Responsible Party | Work Package | Package Code | Tag ID | DWG # | REF RFI # | Comments | Raised Date | Cleared By | Cleared Date | Open / Close | AGE | CLEAR TIME | OLDER THAN 4WEEKS | OLDER THAN 6 WEEKS | OLDER THAN 8 WEEKS
Formulas:
AGE = IF([Open / Close]="","",IF([Open / Close]="Open",TODAY()-[Raised Date],"--"))

## SYSTEM MODEL
SYSTEM MODEL ¦ Functional Systems
True functional System of Interest records (not the operational WORK PACKAGES progress grouping).
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
System ID | Source Code | System Name | System Type | Scope Disposition | Source IDs | Location / Boundary | Review State | Notes

## RFI REGISTER
RFI REGISTER ¦ Authoritative Working RFI Records
Persistent RFI IDs; one row per question. Counts use Primary WP ID to avoid double counting. Historical data requires owner review.
Statuses: Open / Submitted / Answered / Closed / Cancelled; all except Closed and Cancelled count as open. Blank WP remains Unassigned; do not infer.
RFI ID | Question / Clarification Requested | Status | Primary WP ID | Related WP IDs | Related Scope IDs | Source / Document Reference | Responsible Party | Requested By | Date Raised | Required By | Response / Decision | Response Source | Closed Date | Review State | Legacy Reference | Remarks | Blocked? (X)

## ISSUES
ISSUES ¦ Open Items and Findings
Technical findings / gaps needing engineering disposition; operational unfinished-work tasks stay in PUNCH LIST; formal client questions stay in RFI REGISTER.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Item ID | Kind | Statement | Affected IDs | Source IDs | Owner | Resolve By | Status | Priority | Opened Date | Closed Date | Resolution + Source | Legacy Reference | Notes | Primary Scope ID | Affected WP IDs | Blocked? (X)

## PUNCH LIST
Punchlist | Description | Discipline | Responsible Party | Work Package | Package Code (WP ID) | Priority Cat | Tag ID | DWG # | REF RFI # | Comments | Raised By | Raised Date | Cleared By | Cleared Date | Open / Close | AGE | CLEAR TIME | OLDER THAN 4WEEKS | OLDER THAN 6 WEEKS | OLDER THAN 8 WEEKS | Blocked? (X)
Formulas:
AGE = IF([Open / Close]="","",IF([Open / Close]="Open",TODAY()-[Raised Date],"--"))
Note on F2: Choose a human-readable Work Package name from the validated list. Package Code displays the corresponding canonical WP ID.
Note on G2: Displays the canonical Work Package ID corresponding to the selected Work Package name. The selector is a human-readable name, not an ID.

## REGISTRY GUIDE
READ ME ¦ Engineering Record & Work Package Contract
WORK PACKAGES define project execution units (not Systems, Equipment, Scope obligations or SOV items). WP PROGRESS holds entered progress. DASHBOARD, SCOPE DASHBOARD and BLOCKED ITEMS REPORT are derived views.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Section | Instruction | Owner / status
Template version | PROJECT_PER v1.1 blank template (KIS controls-engineering). Copy it into authorized project storage, rename it for the project and record that copy in SOURCES / BASELINES. Never enter project data in the repository copy. | Template
Release designation | v1.1 is a STRUCTURE revision of the blank template (work package definition / progress split, '--' progress convention, derived scope progress). It does not approve or accept any project's engineering content. | Owner-accepted structure
Dashboard | DASHBOARD lists WP IDs entered manually in column A. Calculated columns look up WORK PACKAGES (definition) and WP PROGRESS (status); blank progress stays blank. Columns D, J:O and T are manual and travel with the row. | View; formulas read only
Safe sorting | Filter/sort the entire full-width DASHBOARD list (A:U), never a single column. Calculated fields look up by WP ID. | None
Work Package contract | A Work Package is a bounded, independently managed execution unit with progress and completion criteria, normally handed to one team or person. It can span multiple equipment items, scopes or test procedures. | Framework-owned; instance uses WP-###
Work Package definition | WORK PACKAGES owns WP IDs. A:E = WP ID, Package Code, boundary description, hidden legacy selector (D, used by PUNCH LIST / RFI LEGACY forms) and priority. F:S = parent WP, primary and additional scopes, responsible team/person, method, deliverable, dependencies, progress columns in use, tracking basis, references, review state and notes. T checks that the WP has exactly one WP PROGRESS row. | Definition only; no progress here
WP progress | WP PROGRESS has one row per WP ID, chosen from WORK PACKAGES (dropdown uses named range ValidWorkPackageIDs). Enter percentages (0-1), C&E, SAT, vendor checks, Blocked (X) and comments here. Package code, scope, priority, completion, gate and count columns are formulas. | Entered progress
Progress value convention | Number 0-1 = progress. '--' = column not used for this WP (left out of completion, gates and roll-ups). Blank = not entered. Any other text shows CHECK. A WP's gate is complete when every column it uses is complete. | None
Scope progress | SCOPE DASHBOARD derives scope progress per column as the average over WPs whose Primary Scope is that scope (equal weight). Blank and '--' are excluded; enter 0 for 'in use, not started'. WP Count, WPs Gate Complete and Blocked WPs are derived; the scope Blocked? (X) is human-managed. | No SCOPE PROGRESS tab from v1.1
Parent / child WPs | Parent Work Package ID is a definition field only. v1.1 does not roll child progress into parents; parent progress must not double count children. | None
Splitting work packages | Create a separate WP when the work goes to a different team or person, has its own blocking dependency (e.g. equipment by others), or is a deliverable handed off on its own. Do not create WPs per device or point; that detail belongs in the Equipment/Device/Points workbook. | Guidance
Project record authority | SCOPES, RECORDS, SYSTEM MODEL, SOURCES, LINKS and ISSUES are the project-level registers. Physical equipment/device/point inventory is kept in the separate Equipment/Device/Points workbook. | Cross-file IDs
Linkage | Equipment/Device/Points rows carry Primary Work Package ID, Primary Scope ID and Link Review State as candidates until reviewed; additional relationships use LINKS. Do not copy equipment facts into the PER. | None
Source trail | SOURCES records contract, vendor, field and internal sources; exact revision and source locator required. | None
Names: register wording vs verbatim | In register wording use the project's current names. When a cell quotes something that exists outside the register (a file name, folder or path, a document's own title, or a label printed on a source drawing) copy it exactly and put it in quotes, e.g. a folder named 'Job 1234 - UNIT-01' stays 'UNIT-01' even if the register calls the unit UNIT-1. If the real name changes, update the quote and log it. | None
Imported notes | INTAKE QUEUE holds verbatim prior-work notes/RFI text queued for review; not facts, obligations or new RFIs until reconciled. | None
Record types | RECORDS supports Need, Fact, Requirement, Constraint, Criterion, Assumption, Directive, Decision, Finding. | Scope/work actions are first-class in SCOPES
Unknown != none | Do not enter 0, Not Applicable, or Accepted merely because a source omits something. | Keep unresolved explicitly
Scopes ontology | SCOPES are engineering/drawing/logical groupings that connect WPs into systems. Atomic contractual obligations are maintained as requirements or source-backed records; do not silently reclassify legacy scope IDs. | None
Scope of Work display | DASHBOARD Scope of Work looks up WORK PACKAGES Primary Scope ID; blank until assignments are made. | None
RFI authority | RFI REGISTER is authoritative; RFI LEGACY is a hidden read-only reference for imported legacy RFIs; ISSUES holds engineering findings. | None
RFI counts | Open RFIs count by Primary WP ID (WP PROGRESS!Z). RFIs with a blank Primary WP ID are unassigned, not resolved. Related WPs do not double count. | None
RFI migration | Legacy question text, status, dates, responses and comments are carried forward; migrated RFIs require owner review. | None
Operational tracking vs engineering evidence | PUNCH LIST is an execution action / follow-up queue (unfinished field work, coordination, troubleshooting, corrective actions, blockers); it is not a substitute for ISSUES, RFIs or test acceptance evidence. | Keep registers independent
ISSUES | ISSUES records engineering uncertainties, contradictions, failures and findings requiring technical disposition. Primary authority is Scope ID; Affected WP IDs are explicit. Link records by stable IDs rather than duplicating statements. | Canonical technical finding; not a to-do list
Punch List WP selection | PUNCH LIST Work Package is selected against WORK PACKAGES; the adjacent Package Code is computed as the canonical WP-### via INDEX/MATCH. | Preserve dropdown and formula
Blocking convention | X or blank: human-maintained attention flag in WP PROGRESS, ISSUES, RFI REGISTER, PUNCH LIST and SCOPE DASHBOARD. No auto-propagation; open counts do not determine blocking. BLOCKED ITEMS REPORT is a filterable live projection; filter Record ID to nonblank. | Do not infer blocking from counts
Optional commercial reference | Schedule of Values (SOV) is an optional commercial reference only; no SOV tab, number, cost or payment status is required. | Not applicable by default
Commercial vs technical | Work Package progress, engineering completion, commissioning verification and commercial valuation are different states. Completing internal progress gates is not SAT acceptance. | Preserve independent review states
Changes and history | CHANGE LOG and BASELINES are persistence/archival registries; neither logs edits automatically nor approves a project baseline. A workbook copy is not configuration acceptance. | Populate via controlled process
Protection | Engineering acceptance protects identified derived decisions; snapshot/baseline captures state separately. | No automatic approval on baseline
Baseline custody | Archive each project baseline as a separate immutable file with an external SHA-256 manifest; do not overwrite the project's working copy. | None
Migration | When adopting this template for a project with prior trackers, reconcile contract sources and prior notes/RFIs first, then promote verified records. | M1/M2
Formatting revisions | Applying built-in cell styles is presentation-only if values, formulas, data validation, filter ranges, stable IDs and relationships are unchanged. No version bump for cosmetic edits. | Presentation adjustments authorized
Check tabs | WP CHECKS: structure checks (every WP has exactly one progress row; no orphans, duplicates or CHECK values) and a sample roll-up test. WP FORMULA TESTS: sample cases for the '--' completion and gate formulas. Sample data only; may be hidden in project copies. | Keep with template
Latest framework | https://github.com/kissolutions/knowledgebase_wikijs/blob/main/governance-and-doctrine/systems-engineering-framework-v1.md | Parent framework
Scope work actions | SCOPES!R Work Actions records what is done in the scope using the M1 action vocabulary: furnish, install, remove, replace, modify, rewire, reprogram, integrate, monitor, test, document, coordinate. Several actions are entered separated by '; ' (the dropdown warns but accepts). Blank means not yet established, not none. | M1 scope extraction

## SOURCES
SOURCES ¦ Source Evidence
Source IDs and exact document issue/revision are required before facts or scope obligations are promoted.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Source ID | Document / File | Source Class | Issuer / Authority | Revision | Issue Date | Exact Locator / URL | Received Date | Governs / Topic | Review State | Supersedes ID | Notes

## RECORDS
RECORDS ¦ Engineering Evidence and Requirements
Typed durable Need/Fact/Requirement/Constraint/Criterion/Assumption/Directive/Decision/Finding records.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Record ID | Record Type | Atomic Statement | Applies To IDs | Source IDs | Authority / Binding Basis | Applicability | Confidence | Review State | Owner | Resolve By | Related IDs | Verification Method | Supersedes | Updated | Notes

## LINKS
LINKS ¦ Typed Relationships
Typed cross-record links; WorkPackage tracks_scope Scope links connect progress to contractual obligations.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Link ID | From Type | From ID | Relationship | To Type | To ID | Source IDs | Review State | Notes | Linked Scope State (derived)

## CHANGE LOG
CHANGE LOG ¦ Record Revision Events
Persistent change records must be written during an authorized process; this tab does not log edits automatically.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Change ID | Timestamp | Object Type | Object ID | Action | Old Rev / Value | New Rev / Value | By / Approved By | Source / Basis | Affected IDs | Notes

## BASELINES
BASELINES ¦ Immutable Snapshots
Register snapshot metadata only. Archive a separate immutable file and manifest; a baseline is not blanket approval.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Baseline ID | Milestone | Captured At | Authorized By | Register Revision | Source Manifest | SHA-256 / Hash | Storage Path | Status | Open Items | Notes

## INTAKE QUEUE
INTAKE QUEUE ¦ Legacy Notes and RFIs
Verbatim legacy prior-work content queued for M1/M2 comparison; neither verified nor promoted automatically.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Intake ID | Origin Tab | Origin Row | Verbatim Original Text | Legacy Status | Legacy System | Legacy Tag | Legacy Drawing | Legacy Comment | Suggested Kind | Review State | Promoted Record ID | Source ID | Legacy Cell

## WP CHECKS
WP CHECKS
Structure check | Value | Expected | Result
WP IDs defined in WORK PACKAGES
WP rows in WP PROGRESS
WPs with no progress row |  | 0
WPs with duplicate progress rows |  | 0
Progress rows not in WORK PACKAGES |  | 0
Progress values flagged CHECK |  | 0
Roll-up test (sample data, not project data)
Sample WP | Scope | Eng % |  | Scope | Derived Eng % | Expected | Result
S1 | SX | 1 |  | SX |  | 0.75
S2 | SX | 0.5 |  | SY |  | 0
S3 | SX | --
S4 | SX
S5 | SY | 0
SX: 1 and 0.5 average to 0.75; '--' (not used) and blank (not entered) are left out. SY: 0 counts.
Overall

## WP FORMULA TESTS
Case | Eng (G) | Prog (H) | C&W (I) | Dev (J) | Loop (K) | PreComm (L) | Eng done? | Prog done? | C&W done? | Dev done? | Loop done? | PreComm done? | Gate | Expected gate | Expected Eng done? | PASS? | What it tests
T1 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | Yes | Yes |  | all complete
T2 | 1 | -- | -- | -- | -- | -- | [7 empty] | Yes | Yes |  | Engineering-only WP (WP-ENG) complete
T3 | 0.5 | -- | -- | -- | -- | -- | [7 empty] | No | PARTIAL |  | Engineering-only WP in progress
T4 | -- | -- | -- | -- | -- | -- | [7 empty] | -- | -- |  | WP with nothing in use
T5 | 1 | -- | 1 | -- | -- | -- | [7 empty] | Yes | Yes |  | By-others WP (Eng + Cond & Wire) done
T6 | 1 | -- | 0 | -- | -- | -- | [7 empty] | No | Yes |  | By-others WP (Eng + Cond & Wire): submittal in, wiring not started
T7 |  | -- | -- | -- | -- | -- | [7 empty] | No |  |  | blank Eng is not done
T8 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | No | No |  | nothing started
T9 | n/a | 1 | 1 | 1 | 1 | 1 | [7 empty] | No | CHECK |  | stray text is flagged, not counted as done (old formula said Yes)
T10 | -- | 1 | 1 | 1 | 1 | 1 | [7 empty] | Yes | -- |  | dash with spaces still treated as not used
Result
Rules under test: '--' = column not used / by others, excluded from completion. A WP is complete when every column it uses is done. Blank = not done. Any other text = CHECK. Gate shows No (was '--') when not complete, because '--' now means not used.