## DASHBOARD
PROJECT PROGRESS DASHBOARD
Work Package ID | Package Code | Priority Level | Critical Path? | Eng Completion | Program Completion | Conduit & Wire Pulls | Devices Installed | PreComm Completed | BLOCKED - Eng Info | BLOCKED - Vendor Info | BLOCKED - Cond & Wire | BLOCKED - Devices | BLOCKED - PreComm | Active Change Orders? | Internal Gates Complete? | Open Punchlist Items | Open RFIs | Open Issues | Weekly Notes | Engineering Scope / Scope of Work
WP-001
WP-002
WP-003
WP-004
WP-005
WP-006

## SCOPE DASHBOARD
SCOPE DASHBOARD ¦ ENGINEERING REVIEW
Scope rows are manually identified by Scope ID. Values below are calculated; blocking X is human-managed. No automatic flag propagation.
Scope ID | Engineering Scope | WP Count | Open Issues | Open RFIs | Blocked? (X) | Engineering State

## BLOCKED ITEMS REPORT
PM / PE BLOCKED ITEMS REVIEW
Filter the Record ID column to nonblanks. Each X flag is independent; report does not set or clear flags.
Register | Record ID | Scope ID | Work Package ID(s) | Description / Question / Task | Owner | Status | Blocked (X)

## WORK PACKAGES
Work Package ID | Package Code | Work Boundary Description (draft) | Legacy Selector Label (compatibility) | Priority Sequence | Open Punch Items | Eng % Complete | Prog % Complete | Cond & Wire % Complete | Device Install % Complete | Loop Check % Complete | PreComm % Complete | C&E Values Received | CE Target Test Date | Engineering Completed? | Programming Completed? | Cond & Wire Completed? | Device Install Completed | Loops Check Completed | PreComm Complete? | Program Changes Required | Program changes Completed | Internal Progress Gates Complete? | Site Acceptance Test Complete? | Vendor Completed Checks | Comments | Parent Work Package ID (optional) | Supplemental Boundary Notes (owner input) | Test Procedure Ref (optional) | Closeout Evidence Ref (optional) | Relationship Review State | Tracking Basis | Open RFIs (Primary WP) | Unassigned Open RFIs (Project) | Primary Engineering Scope ID | Additional Scope IDs (optional) | Blocked? (X) | Open Engineering Issues
WP-001 | DOAS-1 | DOAS-1 controls and associated implementation activities tracked together for progress. Included devices, damper interfaces and acceptance boundaries require M1/M2 reconciliation. | DOAS-1 | [26 empty] | Source and relationships pending M1/M2 review | equipment-led
WP-002 | EF-1 | EF-1 exhaust controls and associated VFD configuration/integration work, including separate fan and drive test activities where applicable. Final work-package split remains under review. | EF-1 | [23 empty] | Owner input: VFD setup / separate conduit work; verify exact package boundary at M1. | Owner input: distinct VFD test workflow; procedure reference pending. |  | Source and relationships pending M1/M2 review | equipment-led
WP-003 | VRF | VRF system controls integration across associated equipment. Confirm covered units, interfaces, responsibilities and acceptance tasks against contract and vendor sources. | VRF System | [26 empty] | Source and relationships pending M1/M2 review | system-led
WP-004 | ISO-DPR-1 | ISO-DPR-1 isolation damper assembly controls with multiple signals and independent functional verification. DOAS functional relationship does not imply a merged work package. | ISO-DPR-1 | [23 empty] | Owner input: damper assembly with multiple signals; verify source scope and I/O. | Owner input: independently tested damper; procedure reference pending. |  | Source and relationships pending M1/M2 review | equipment-led
WP-005 | ISO-DPR-2 | ISO-DPR-2 isolation damper assembly controls with multiple signals and independent functional verification. DOAS functional relationship does not imply a merged work package. | ISO-DPR-2 | [23 empty] | Owner input: damper assembly with multiple signals; verify source scope and I/O. | Owner input: independently tested damper; procedure reference pending. |  | Source and relationships pending M1/M2 review | equipment-led
WP-006 | ROOM | Room monitoring functions and associated devices, signals and test work. Room roster, installation boundaries and interfaces remain subject to M1/M2 reconciliation. | Room Monitoring | [26 empty] | Source and relationships pending M1/M2 review | function-led

## RFI REGISTER
RFI REGISTER ¦ Authoritative Working RFI Records
Persistent RFI IDs; one row per question. Counts use Primary WP ID to avoid double counting. Historical data requires owner review.
Statuses: Open / Submitted / Answered / Closed / Cancelled; all except Closed and Cancelled count as open. Blank WP remains Unassigned; do not infer.
RFI ID | Question / Clarification Requested | Status | Primary WP ID | Related WP IDs | Related Scope IDs | Source / Document Reference | Responsible Party | Requested By | Date Raised | Required By | Response / Decision | Response Source | Closed Date | Review State | Legacy Reference | Remarks | Blocked? (X)
RFI-0001 | We have more VRF components in the vendor submittals than VRF systems highlighted in the scope markup | Open | WP-003 | [5 empty] | 2024-10-20 |  |  |  |  | Imported - needs owner review | RFI LEGACY!C3
RFI-0002 | Do we want to use the VRF Indoor Unit ON/OFF features of the MIM-14B contact card? Or leave it jumpered to always enable. ** common use case would be hotel keycard enablement by the room door. | Open | [6 empty] | 2024-10-20 |  |  |  |  | Imported - needs owner review | RFI LEGACY!C4
RFI-0003 | There is a note: "PROVIDE DDC CONTROLS TO MODULATE DAMPERS TO BRING ON REDUNDANT UNIT, AND MAINTAIN 70 DEGREES @50% RH SPACE CONDITION" on the markups. It points at the OA intake wall louver for the VRF system. Is this actually for the DOAS unit or is the the 2nd Kitchen VRF unit redundant? | Open | [6 empty] | 2024-10-22 |  |  |  |  | Imported - needs owner review | RFI LEGACY!C5
RFI-0004 | What is our integration scope on AHU-3, AHU-4 replacements? | Open | [11 empty] | Imported - needs owner review | RFI LEGACY!C6
RFI-0005 | Which room are we monitoring Temperature/Humidity in? | Open | [11 empty] | Imported - needs owner review | RFI LEGACY!C7
RFI-0006 | Which room are we monitoring Differential Pressure? | Open | [11 empty] | Imported - needs owner review | RFI LEGACY!C8
RFI-0007 | DOAS unit states "Bacnet MSTP monitoring", but seems to have an RJ45 Protocessor board like the BTU meters. MSTP or Ethernet? | Open | WP-001 | [10 empty] | Imported - needs owner review | RFI LEGACY!C9

## RFI LEGACY (hidden)
Punchlist | Description | Discipline | Responsible Party | Work Package | Package Code | Tag ID | DWG # | REF RFI # | Comments | Raised Date | Cleared By | Cleared Date | Open / Close | AGE | CLEAR TIME | OLDER THAN 4WEEKS | OLDER THAN 6 WEEKS | OLDER THAN 8 WEEKS
1 | We have more VRF components in the vendor submittals than VRF systems highlighted in the scope markup | SoW |  | VRF System | [5 empty] | 4558500% |  |  | Open |  |  | 1 | 1 | 1
| Do we want to use the VRF Indoor Unit ON/OFF features of the MIM-14B contact card? Or leave it jumpered to always enable. ** common use case would be hotel keycard enablement by the room door. | SoW | [7 empty] | 4558500% |  |  | Open |  |  | 1 | 1 | 1
| There is a note: "PROVIDE DDC CONTROLS TO MODULATE DAMPERS TO BRING ON REDUNDANT UNIT, AND MAINTAIN 70 DEGREES @50% RH SPACE CONDITION" on the markups. It points at the OA intake wall louver for the VRF system. Is this actually for the DOAS unit or is the the 2nd Kitchen VRF unit redundant? | SoW | [7 empty] | 4558700% |  |  | Open |  |  | 1 | 1 | 1
| What is our integration scope on AHU-3, AHU-4 replacements? | SoW | [10 empty] | Open |  |  | 1 | 1 | 1
| Which room are we monitoring Temperature/Humidity in? | SoW | [10 empty] | Open |  |  | 1 | 1 | 1
| Which room are we monitoring Differential Pressure? | SoW | [13 empty] | 1 | 1 | 1
| DOAS unit states "Bacnet MSTP monitoring", but seems to have an RJ45 Protocessor board like the BTU meters. MSTP or Ethernet? | SoW |  | DOAS-1 | [11 empty] | 1 | 1 | 1
[16 empty] | 1 | 1 | 1
[16 empty] | 1 | 1 | 1
[16 empty] | 1 | 1 | 1
[16 empty] | 1 | 1 | 1
[16 empty] | 1 | 1 | 1
[16 empty] | 1 | 1
[16 empty] | 1 | 1 | 1
[16 empty] | 1 | 1
[16 empty] | 1 | 1
[16 empty] | 1 | 1
[16 empty] | 1 | 1 | 1
[16 empty] | 1 | 1
1
1
1
1
200
[16 empty] | 1 | 1
Formulas:
AGE = IF([Open / Close]="","",IF([Open / Close]="Open",TODAY()-[Raised Date],"--"))

## PUNCH LIST
Punchlist | Description | Discipline | Responsible Party | Work Package | Package Code (WP ID) | Priority Cat | Tag ID | DWG # | REF RFI # | Comments | Raised By | Raised Date | Cleared By | Cleared Date | Open / Close | AGE | CLEAR TIME | OLDER THAN 4WEEKS | OLDER THAN 6 WEEKS | OLDER THAN 8 WEEKS | Blocked? (X)
1 | [14 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
[15 empty] | Open |  |  | 1 | 1
[15 empty] | Open |  |  | 1 | 1 | 1
Open
Open
Open
Open
Open
Open
[15 empty] | Open |  |  | 1 | 1
[18 empty] | 1 | 1
[18 empty] | 1 | 1
[18 empty] | 1 | 1 | 1
[18 empty] | 1 | 1
1
1
1
1
200
[18 empty] | 1 | 1
Formulas:
AGE = IF([Open / Close]="","",IF([Open / Close]="Open",TODAY()-[Raised Date],"--"))
Note on F2: Choose a human-readable Work Package name from the validated list. Package Code displays the corresponding canonical WP ID.
Note on G2: Displays the canonical Work Package ID corresponding to the selected Work Package name. The selector is a human-readable name, not an ID.

## REGISTRY GUIDE
READ ME ¦ Engineering Record & Work Package Contract
WORK PACKAGES are project-defined execution units (not Systems, Equipment, Scope obligations or SOV items). DASHBOARD and SCOPE PROGRESS remain derived views.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Section | Instruction | Owner / status
Working file / version | PM TRACKER v1.0 (2026-10-20). Established project-management workbook structure and canonical register contract. Engineering source extraction, assignments, and acceptance states remain subject to review. Original Google Drive PM TRACKER is not replaced. | v1.0 structural baseline; source reconciliation ongoing
Original reporting | DASHBOARD retains six legacy work-group labels through a hidden compatibility selector. Work Package identity is WP-###, not equipment or system naming. | Progress metrics and original RFI/punchlist inputs retained
Scope progress | SCOPE PROGRESS reads the WORK PACKAGES progress master and counts only reviewed WorkPackage tracks_scope Scope relationships entered in LINKS. | View only; do not edit formulas
Project record authority | SCOPES, RECORDS, SYSTEM MODEL, SOURCES, LINKS, ISSUES are proposed project-level registers; EQUIPMENT, DEVICES and POINTS draft tabs removed. | Physical inventory is kept in the separate ASSETS.xlsx
Source trail | SOURCES records contract, vendor, field and internal sources; exact revision and source locator required. | SRC-LEGACY-001 = original internal workbook only
Imported notes | INTAKE QUEUE contains verbatim prior NOTES/RFI descriptions; all unreviewed. | Not facts, obligations, or new RFIs until reconciled
Linkage and ASSETS | ASSETS EQ LIST has filterable Primary Work Package ID, Primary Scope ID and Link Review State fields. Primary links are candidates until reviewed; additional relationships may use project LINKS. | Cross-file IDs; no copy of equipment facts into PM TRACKER
Record types | RECORDS supports Need, Fact, Requirement, Constraint, Criterion, Assumption, Directive, Decision, Finding. | Scope/work actions are first-class in SCOPES
Unknown != none | Do not enter 0, Not Applicable, or Accepted merely because a source omits something. | Keep unresolved explicitly
Changes and history | CHANGE LOG and BASELINES are proposed persistence/archival registries; neither is an automatic log or approved project baseline. Do not treat a workbook copy as configuration acceptance. | Populate via controlled process / automation
Protection | Engineering acceptance protects identified derived decisions; snapshot/baseline captures state separately. | No automatic approval on baseline
Migration | First reconcile all M95 contract sources and older PM TRACKER notes/RFIs; then promote verified records. | M1/M2 pilot
Work Package contract | A Work Package is a bounded, independently managed execution group with progress and completion criteria. It can span multiple equipment items, scopes or test procedures. | Framework-owned; domain instance uses WP-###
Work Package fields | WORK PACKAGES!A:C = Work Package ID, Package Code and draft boundary description. D is a hidden legacy selector for existing NOTES/RFI/PUNCH LIST forms; AG preserves the earlier Tracking Basis. | Do not enter SOV or invent acceptance from progress
Optional commercial reference | Schedule of Values (SOV) is a framework-recognized optional commercial reference only. M95 has no assumed SOV; no SOV tab, number, cost or payment status is required. | Not applicable by default / do not populate
Owner-provided context | EF-1 VFD setup and ISO-DPR damper assembly/test independence are owner-described examples, entered as unverified context. Verify contractual scope, detailed procedures and IDs in M1/M2. | Source/relationships pending verification
Rollup policy | ISO-DPR-1/2 may be grouped under DOAS-1 later, but no Parent Work Package or equipment containment is asserted today. Parent progress must not double count children. | No grouping decision recorded
Commercial vs technical | Work Package progress, engineering completion, commissioning verification and commercial valuation are different states. Completing internal progress gates is not SAT acceptance. | Preserve independent review states
Latest framework | https://github.com/kissolutions/knowledgebase_wikijs/blob/46b8b3ed75d47fdc391f58379d232546e3175633/governance-and-doctrine/systems-engineering-framework-v1.md | Source revision for this review copy
Review status | Draft split: PM TRACKER for project records; ASSETS for equipment/device inventory. New ASSETS WP assignments are candidates based on existing tags; Scope ID blank until M1. | DRAFT — not promoted to authoritative Drive source
Asset inventory delivery | ASSETS EQ LIST remains a standalone handoff with original equipment/device information intact. The blank draft PM POINTS table was not an I/O schedule; actual point deliverable must be sourced separately. | No physical point records discarded
RFI authority | RFI REGISTER is authoritative; RFI LEGACY is hidden read-only reference; ISSUES remains general engineering findings.
RFI dashboard | DASHBOARD!S uses primary WP ID, with unassigned RFIs counted in WORK PACKAGES!AI2. Related WPs do not double count.
RFI migration | Legacy question text, status, dates, response/comments are carried forward. All migrated RFIs require owner review; blank WP means unassigned, not resolved.
Operational tracking vs engineering evidence | PUNCH LIST is an execution action / follow-up queue (unfinished field work, coordination, troubleshooting, post-test corrective actions, blockers); it is NOT a substitute for engineering ISSUES, RFIs or test acceptance evidence. | Keep operational register independent; structure enhancement pending owner review
ISSUES | ISSUES records engineering uncertainties, contradictions, failures, and findings requiring technical disposition. One Issue may lead to zero or many operational tasks; link records by stable IDs rather than duplicating their statements. | Canonical technical finding; not a to-do list
Legacy NOTES disposition | NOTES worksheet retired after its nonempty entries were already preserved as review candidates in INTAKE QUEUE (INT-0001 through INT-0004). Do not elevate them to verified facts until reviewed. | Legacy original retained separately in source workbook
Dashboard row identity | Dashboard is a manually maintained commissioning-meeting list. Enter unique WP-### IDs in column A; the sheet does not dynamically generate/reorder those rows.
Scope of Work display | Dashboard Scope of Work is a lookup of WORK PACKAGES Primary Engineering Scope ID; values remain blank until reviewed assignments are made. Filter/sort complete Work Package rows only.
Safe sorting | Dashboard Work Package IDs are manually entered and stable; filter/sort the entire full-width Dashboard list (currently A:U), never a single column. Calculated fields look up by WP ID; manual blockers, change orders and meeting notes travel with the row.
Scopes ontology | SCOPES now refers to engineering/drawing/logical scopes that group Work Packages into a functional system. Atomic contractual obligations must be maintained as requirements or source-backed records; do not silently reclassify legacy scope IDs.
Blocking convention (PM / PE) | X or blank: human-maintained attention flag in WORK PACKAGES, ISSUES, RFI REGISTER, PUNCH LIST and SCOPE DASHBOARD. No auto-propagation. BLOCKED ITEMS REPORT is a filterable live formula projection; filter Record ID to nonblank.
Issue mapping | ISSUES primary authority is Scope ID; Affected WP IDs are explicit. Open counts do not determine blocking.
Release designation | v1.0 is the first accepted workbook STRUCTURE baseline for M95. It is not an approval or acceptance of engineering requirements, source extracts, asset mappings, RFIs, tests or commissioning progress. | Owner requested uprev, 2026-10-20
Work Package / Scope hierarchy | WORK PACKAGES are the actively managed commissioning/PM units identified by WP-###. SCOPES are engineering/drawing/logical groupings that connect WPs into systems; source-backed obligations remain traceable separately. | Current project convention
Punch List WP selection | PUNCH LIST Work Package name is selected using validation against WORK PACKAGES; adjacent Package Code is computed as canonical WP-### via INDEX/MATCH. | Preserve dropdown and formula
Blocking / open-item counts | X/blank blocking flags are human-maintained and independent. DASHBOARD shows open operational actions, RFIs and affected engineering ISSUES by WP. SCOPE DASHBOARD provides engineering-level summary. | Do not infer blocking from counts
Operational vs engineering issues | PUNCH LIST tracks actionable unfinished work, testing follow-up and coordination. ISSUES tracks unresolved engineering/design/source/approval concerns. RFIs are formal questions to stakeholders. | Do not merge these registers
Formatting revisions | Applying Excel built-in Calculation, Output, Note and similar styles is presentation-only if values, formulas, data validation, table/filter ranges, stable IDs and relationships are unchanged. No version bump necessary for cosmetic edits. | Presentation adjustments authorized
Baseline custody | Archive M95_PM_TRACKER_v1.0.xlsx together with its external SHA-256 manifest; do not treat this file as having replaced the original on Google Drive. Update archived baseline only through an explicit new revision. | Local copy; no Drive overwrite

## SCOPE PROGRESS
SCOPE PROGRESS ¦ Work Package View
Progress values are retained from WORK PACKAGES; scope counts include reviewed WP-to-Scope links only.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Work Package | Package Code | Priority | Engineering % | Programming % | Conduit & Wire % | Devices % | Pre-Comm % | Linked Scopes | Scopes Complete | Scope Count % | Open Issues | Status / Review Note
Scope % counts completed obligations equally; not effort-weighted. WP links require review.
Scope % counts completed obligations equally; not effort-weighted. WP links require review.
Scope % counts completed obligations equally; not effort-weighted. WP links require review.
Scope % counts completed obligations equally; not effort-weighted. WP links require review.
Scope % counts completed obligations equally; not effort-weighted. WP links require review.
Scope % counts completed obligations equally; not effort-weighted. WP links require review.

## SOURCES
SOURCES ¦ Source Evidence
Source IDs and exact document issue/revision are required before facts or scope obligations are promoted.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Source ID | Document / File | Source Class | Issuer / Authority | Revision | Issue Date | Exact Locator / URL | Received Date | Governs / Topic | Review State | Supersedes ID | Notes
SRC-LEGACY-001 | PM TRACKER.xlsx | Internal prior work | KIS / Klutch (project internal) | 2026-10-16 imported copy |  | https://docs.google.com/spreadsheets/d/1GCr9D32eXvYCFW_mE13U1mPDOKZaZqD5/edit | 2026-10-19 | Existing project tracking, notes and RFIs | unreviewed |  | Not an external contract or technical authority; original untouched.

## SCOPES
SCOPES ¦ Engineering System / Drawing / Logical Scope
Engineering scopes organize multiple Work Packages into a coherent functional system or issued drawing/logic package. Scope members and requirements are traced by ID.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Scope ID | Engineering Scope / System Description | Functional / Drawing Boundary | Lead Discipline / Responsible Party | Primary System ID (optional) | Related Work Package IDs (summary) | Disposition | Source / Requirement IDs | Engineering Basis / Authority | Review State | Engineering State | Engineering Progress % (if applicable) | Owner | Target Date | Related IDs | Notes | Updated

## RECORDS
RECORDS ¦ Engineering Evidence and Requirements
Typed durable Need/Fact/Requirement/Constraint/Criterion/Assumption/Directive/Decision/Finding records.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Record ID | Record Type | Atomic Statement | Applies To IDs | Source IDs | Authority / Binding Basis | Applicability | Confidence | Review State | Owner | Resolve By | Related IDs | Verification Method | Supersedes | Updated | Notes

## SYSTEM MODEL
SYSTEM MODEL ¦ Functional Systems
True functional System of Interest records (not the operational WORK PACKAGES progress grouping).
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
System ID | Source Code | System Name | System Type | Scope Disposition | Source IDs | Location / Boundary | Review State | Notes

## LINKS
LINKS ¦ Typed Relationships
Typed cross-record links; WorkPackage tracks_scope Scope links connect progress to contractual obligations.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Link ID | From Type | From ID | Relationship | To Type | To ID | Source IDs | Review State | Notes | Linked Scope State (derived)

## ISSUES
ISSUES ¦ Open Items and Findings
Technical findings / gaps needing engineering disposition; operational unfinished-work tasks stay in PUNCH LIST; formal client questions stay in RFI REGISTER.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Item ID | Kind | Statement | Affected IDs | Source IDs | Owner | Resolve By | Status | Priority | Opened Date | Closed Date | Resolution + Source | Legacy Reference | Notes | Primary Scope ID | Affected WP IDs | Blocked? (X)

## CHANGE LOG
CHANGE LOG ¦ Record Revision Events
Persistent change records must be written during an authorized process; this tab does not log edits automatically.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Change ID | Timestamp | Object Type | Object ID | Action | Old Rev / Value | New Rev / Value | By / Approved By | Source / Basis | Affected IDs | Notes
CHG-001 | 2026-10-19 | PM TRACKER Schema | WORK PACKAGES / REGISTRY GUIDE | draft schema alignment | 21-tab Work Packages Review | 21-tab Framework-Aligned Review | ChatGPT — design draft, unapproved | KIS systems engineering framework commit 46b8b3e | WP-001..WP-006; no scope, test acceptance or system/equipment IDs altered | Added optional parent/test/evidence references; owner-provided context labeled unverified; SOV explicitly optional. Original PM TRACKER unchanged.
CHG-002 | 2026-10-20 | Project workbook / inventory split | WORK PACKAGES + ASSETS | draft schema alignment | 21-sheet Excel-clean review copy | 18-sheet PM TRACKER + separate ASSETS link fields | ChatGPT — proposed for owner review | KIS shared framework 46b8b3e and owner direction | WP-001..WP-006; original ASSETS EQ tags | Removed empty EQUIPMENT/DEVICES/POINTS PM tabs; WP A:C standardized; hidden legacy selector maintained; 10 candidate primary WP mappings proposed in ASSETS, no Scope IDs assigned.
CHG-004 | 2026-10-20 | RFI Register | RFI REGISTER / RFI LEGACY | draft registry migration | Legacy RFI and ISSUES model | Canonical RFI rows and WP-linked counts | ChatGPT — pending owner review | Owner direction: project RFI system | Existing RFIs retained; no status forced closed | Added RFI REGISTER and dashboard counts; legacy sheet hidden; unassigned remains visible
CHG-005 | 2026-10-20 | Workbook cleanup / governance | NOTES / _Status Table / zzDASHBOARD | retire legacy worksheets | 19-sheet RFI-aligned review | 16-sheet operations review | ChatGPT draft - owner review | Owner instruction | INT-0001..INT-0004; ISSUES; PUNCH LIST | Removed two obsolete template tabs and NOTES after prior intake copy; preserved PUNCH LIST as an operations register pending design review
2026-10-20 | DASHBOARD WP identity and Scope model | Manual WP IDs; key-based lookup; sortable primary engineering Scope ID; no inferred scope assignments
CHG-006 | 2026-10-20 | PM TRACKER baseline | PM TRACKER / REGISTRY GUIDE / BASELINES | release v1.0 | M95_PM_TRACKER_PUNCH_WP_VALIDATED.xlsx | M95_PM_TRACKER_v1.0.xlsx | Owner requested version; structural acceptance only | Conversation: uprev PM TRACKER to v1.0 | WP-001..WP-006; all 18 workbook tabs | No engineering records marked accepted; presentation-only future styles not substantive revisions.

## BASELINES
BASELINES ¦ Immutable Snapshots
Register snapshot metadata only. Archive a separate immutable file and manifest; a baseline is not blanket approval.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Baseline ID | Milestone | Captured At | Authorized By | Register Revision | Source Manifest | SHA-256 / Hash | Storage Path | Status | Open Items | Notes
BL-001 | PM TRACKER v1.0 structure | 2026-10-20 | Owner direction in project chat | v1.0 | M95_PM_TRACKER_v1.0_manifest.json |  | M95_PM_TRACKER_v1.0.xlsx | STRUCTURE BASELINE; ENGINEERING DATA UNREVIEWED | M1 scope/source reconciliation; user Excel styling | Structural workbook snapshot only; integrity hash is external in manifest to avoid self-referential hash. Original shared Drive workbook untouched.

## INTAKE QUEUE
INTAKE QUEUE ¦ Legacy Notes and RFIs
Verbatim legacy prior-work content queued for M1/M2 comparison; neither verified nor promoted automatically.
Blue = editable • Green = imported prior work • Orange = needs review • Formulas = read only
Intake ID | Origin Tab | Origin Row | Verbatim Original Text | Legacy Status | Legacy System | Legacy Tag | Legacy Drawing | Legacy Comment | Suggested Kind | Review State | Promoted Record ID | Source ID | Legacy Cell
INT-0001 | NOTES | 3 | EF-1 serves Restroom 1.102A, Snorkel, (2) Hoods | [5 empty] | Fact candidate | unreviewed |  | SRC-LEGACY-001 | NOTES!B3
INT-0002 | NOTES | 4 | Remove AHU-2, replace with VRF System | [5 empty] | Fact candidate | unreviewed |  | SRC-LEGACY-001 | NOTES!B4
INT-0003 | NOTES | 5 | MIM-B14(U) DDC Control Board -> MIM-A00UN Subharness -> Indoor Units | [5 empty] | Fact candidate | unreviewed |  | SRC-LEGACY-001 | NOTES!B5
INT-0004 | NOTES | 6 | Which room are we monitoring Temperature/Humidity in? | [5 empty] | Fact candidate | unreviewed |  | SRC-LEGACY-001 | NOTES!B6
INT-0005 | RFI | 3 | We have more VRF components in the vendor submittals than VRF systems highlighted in the scope markup | Open | VRF System |  |  |  | Issue candidate | unreviewed |  | SRC-LEGACY-001 | RFI!C3
INT-0006 | RFI | 4 | Do we want to use the VRF Indoor Unit ON/OFF features of the MIM-14B contact card? Or leave it jumpered to always enable. ** common use case would be hotel keycard enablement by the room door. | Open |  |  |  |  | Issue candidate | unreviewed |  | SRC-LEGACY-001 | RFI!C4
INT-0007 | RFI | 5 | There is a note: "PROVIDE DDC CONTROLS TO MODULATE DAMPERS TO BRING ON REDUNDANT UNIT, AND MAINTAIN 70 DEGREES @50% RH SPACE CONDITION" on the markups. It points at the OA intake wall louver for the VRF system. Is this actually for the DOAS unit or is the the 2nd Kitchen VRF unit redundant? | Open |  |  |  |  | Issue candidate | unreviewed |  | SRC-LEGACY-001 | RFI!C5
INT-0008 | RFI | 6 | What is our integration scope on AHU-3, AHU-4 replacements? | Open |  |  |  |  | Issue candidate | unreviewed |  | SRC-LEGACY-001 | RFI!C6
INT-0009 | RFI | 7 | Which room are we monitoring Temperature/Humidity in? | Open |  |  |  |  | Issue candidate | unreviewed |  | SRC-LEGACY-001 | RFI!C7
INT-0010 | RFI | 8 | Which room are we monitoring Differential Pressure? | [5 empty] | Issue candidate | unreviewed |  | SRC-LEGACY-001 | RFI!C8
INT-0011 | RFI | 9 | DOAS unit states "Bacnet MSTP monitoring", but seems to have an RJ45 Protocessor board like the BTU meters. MSTP or Ethernet? |  | DOAS-1 |  |  |  | Issue candidate | unreviewed |  | SRC-LEGACY-001 | RFI!C9